## Gantt
MaziwaTrack Project Gantt Chart
| Project start | 2026-10-21 |  | How to use: edit only the yellow cells (blue text): Duration, Depends on, Fixed start, % Done, Deadline.
| Today | 2026-10-21 |  | Start and End dates are calculated automatically: a task starts the next working day after the task it depends on, and weekends are skipped.
| Final deadline | 2026-11-25 |  | Bars: light green = planned, dark green = completed part, red = milestone, yellow column = today, grey = weekend.
Progress synced from GitHub on 21 Oct 2026 11:06 (latest commit e4381e5). Tag commits like [T4 60%] or [T4 done].
[13 empty] | Oct | [10 empty] | Nov | [29 empty] | Dec
ID | Task | Phase | Owner | Duration (work days) | Depends on (ID) | Fixed start (optional) | Start | End | % Done | Status | Deadline (optional) | Deadline check | time axis 2026-10-21 to 2026-12-04
1 | Set up repository, folders and .env | Deliverable 3 | Tonybrian | 1 |  |  | 2026-10-21 | 2026-10-21 | 0% | In progress
2 | Create PostgreSQL database (schema.sql, seed.sql) | Deliverable 3 | Tonybrian | 2 | 1 |  | 2026-10-22 | 2026-10-23 | 0% | Not started
3 | Login, registration and roles (bcrypt, JWT, middleware) | Deliverable 3 | Tonybrian | 3 | 2 |  | 2026-10-26 | 2026-10-28 | 0% | Not started
4 | Farmer screen: record deposit and batch number | Deliverable 3 | Angelo | 3 | 1 |  | 2026-10-22 | 2026-10-26 | 0% | Not started
5 | Grader screen: verify quantity and quality | Deliverable 3 | Angelo | 2 | 4 |  | 2026-10-27 | 2026-10-28 | 0% | Not started
6 | Admin screen: view batches and approve payment | Deliverable 3 | Angelo | 3 | 5 |  | 2026-10-29 | 2026-11-02 | 0% | Not started
7 | API: batches, verification and payments | Deliverable 3 | Tonybrian | 3 | 3 |  | 2026-10-29 | 2026-11-02 | 0% | Not started
8 | Connect front-end and admin panel to the database | Deliverable 3 | All | 2 | 7 |  | 2026-11-03 | 2026-11-04 | 0% | Not started
9 | Deliverable 3: mid-semester marking | Milestone | All | 1 | 8 |  | 2026-11-05 | 2026-11-05 | 0% | Not started
10 | Payment email notification | Deliverable 4 | Tonybrian | 2 | 7 |  | 2026-11-03 | 2026-11-04 | 0% | Not started
11 | Receipts and PDF reports (logo, date, filters) | Deliverable 4 | Angelo | 3 | 9 |  | 2026-11-06 | 2026-11-10 | 0% | Not started
12 | Audit log view | Deliverable 4 | Tonybrian | 2 | 9 |  | 2026-11-06 | 2026-11-09 | 0% | Not started
13 | Validation, error messages and help page | Deliverable 4 | Angelo | 2 | 12 |  | 2026-11-10 | 2026-11-11 | 0% | Not started
14 | Testing (unit, API, end-to-end) and bug fixes | Deliverable 4 | Jeremy | 4 | 13 |  | 2026-11-12 | 2026-11-17 | 0% | Not started
15 | User manual and documentation | Deliverable 4 | Jeremy | 4 | 9 |  | 2026-11-06 | 2026-11-11 | 0% | Not started
16 | Deploy (Vercel, Render, hosted PostgreSQL) | Deliverable 4 | Tonybrian | 2 | 14 |  | 2026-11-18 | 2026-11-19 | 0% | Not started
17 | Buffer: fixes and should-have features | Deliverable 4 | All | 2 | 16 |  | 2026-11-20 | 2026-11-23 | 0% | Not started
18 | Presentation rehearsal | Deliverable 4 | All | 1 | 17 |  | 2026-11-24 | 2026-11-24 | 0% | Not started
19 | Deliverable 4: final presentation | Milestone | All | 1 | 18 |  | 2026-11-25 | 2026-11-25 | 0% | Not started | 2026-11-25 | On time
Note on C2: Change this date and every task moves automatically.
Note on C4: Classes end 25 Nov 2026 (from the team). Used as the Deliverable 4 deadline.